## Sheet1
| IAC Internship Program 2023 - Web Development - Development Log |  |  |  | Project Name - Campus Search
Project Manager - Harshada Topale
Intern ID - 4024
Sr | Problem Statement | Task | Details | Date | Status | Comments
1 | Campus Search
1.1 |  | Database Design | Designed the database schema for storing college data (College Name, Address, Courses, Contact Info). | 2024-08-16 | Completed | Ensured accurate structuring of relational database to avoid redundant data.
1.2 |  | Frontend Design - Home Page | Created a responsive home page (index.html) with a search function for users to input their college queries. | 2024-08-18 | Completed | Focused on smooth UI/UX with clean design and user-friendly elements.
1.3 |  | Frontend Design - Results Page | Developed results.html to display the search results, showing relevant colleges based on search criteria. | 2024-08-18 | Completed | Ensured search results were displayed clearly and concisely, optimized for both mobile and desktop views.
1.4 |  | Frontend Design - Contact Page | Created contact.html, providing users with college contact details and additional inquiry options. | 2024-08-19 | Completed | Focused on clarity in layout and accessible design for all users.
1.5 |  | Backend Development | Developed backend API to handle search queries and connect to the database for real-time results. | 2024-08-19 | Completed | Ensured smooth data retrieval and performance optimization.
1.6 |  | Testing - UI/UX | Began testing the application for UI/UX design consistency and responsiveness across devices. | 2024-08-21 | Completed | Minor inconsistencies with mobile responsiveness found; working on fixes.
1.7 |  | Testing - Functionality | Conducted functional testing to ensure the search function retrieves accurate results from the database. | 2024-08-22 | Completed | Some bugs identified in the search algorithm, being addressed in this phase.