## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Web Development
INTERN NAME: | Atharv Musale
PROJECT NAME: | Campus Search
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | DD-MMM-YYYY
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Campus Search |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | IP-4024
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2024-08-01 | Difficulty in setting up a responsive design for the website | Design | Yes | Start with a mobile-first approach and use CSS frameworks like Bootstrap to streamline responsiveness | Revised CSS to ensure all elements were responsive across devices | Project Developer | Solved | Initial design issues delayed project progress by a day
2 | 2024-08-12 | Inconsistencies in the database for college data (missing or outdated information) | Data Management | Yes | Implement data validation checks and schedule regular database updates | Manually updated the database and added validation scripts | Project Developer | Solved | Verified that all entries are now up-to-date
3 | 2024-08-20 | JavaScript functions not working correctly when searching for colleges | Technical | No | Conduct more thorough testing during the development phase and break down functions into smaller testable units | Debugged JavaScript code and modularized functions for better readability and testing | Project Developer | Solved | Improved the search feature's performance
4 | 2024-08-28 | Difficulty in deploying the web application on the chosen hosting platform | Deployment | No | Research deployment options early in the project and consider using platforms like GitHub Pages or Netlify for simple web projects | Chose an alternative hosting platform and followed step-by-step deployment guide | Project Developer | Solved | Final deployment was successful
5 | 2024-08-30 | User feedback indicated the UI was not intuitive | UI/UX | Yes | Conduct user testing sessions early and gather feedback to guide design changes | Redesigned parts of the UI based on user feedback to improve navigation | Project Developer | Solved | Positive feedback received after UI improvements
6 | 2024-08-29 | Slow loading times for pages due to large image files | Performance | No | Optimize images for the web by reducing file sizes without compromising quality | Compressed images and implemented lazy loading | Project Developer | Solved | Page load speed improved significantly