## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
IAC Internship Progra 2023 - Web Development Project Schedule
|  | PROJECT START DATE | 2024-07-21
|  | Display Week Sr No | 1
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments
1 | Week 1: Project Initialization
1.1.1 |  | Planning | Requirement Gathering | - | - | Developer | 2024-07-21 | 2024-07-22 | 2024-07-22 | 3Hrs | Completed | 100 | Requirements gathered from stakeholders regarding features
1.1.1 |  |  | Technology Stack Selection | - | Task 1.1.1 | Developer | 2024-07-22 | 2024-07-23 | 2024-07-24 | 6Hrs | Completed | 100 | Chose HTML, CSS, JavaScript for frontend, and SQL for database
1.2 |  | Project Setup | Setup Git Repository | - | Task 1.1.2 | Developer | 2024-07-24 | 2024-07-25 | 2024-07-26 | 4Hrs | Completed | 100 | Created a project repository and set up version control
1.3 |  | Project Documentation | Initial Documentation | - | - | Developer | 2024-07-26 | 2024-07-26 | 2024-07-27 | 3Hrs | Completed | 100 | Prepared initial project documentation outlining goals
2 | Week 2: Design Phase
3.1.1 |  | Frontend Design | Home Page Design | Create Homepage Layout | Task 1.3.1 | Developer | 2024-07-28 | 2024-07-30 | 2024-07-31 | 10Hrs | Completed | 100 | Responsive homepage designed with navigation, banner, and CTA
2.1.2 |  |  | Results Page Design | Design Search Bar | Task 2.1.1 | Developer | 2024-07-31 | 2024-08-02 | 2024-08-03 | 7Hrs | Completed | 100 | Search bar designed for filtering results
3 | Week 3: Backend Development
3.1.1 |  | Backend Development | Database Implementation | Populate College Data | - | Developer | 2024-08-05 | 2024-08-06 | 2024-08-07 | 10Hrs | Completed | 100 | College database populated with relevant data
3.1.2 |  |  | Search Functionality |  | - | Developer | 2024-08-07 | 2024-08-07 | 2024-08-08 | 6Hrs | Completed | 100
3.2 |  | Contact Form | Design Contact Form | Backend Email Handling | Task 3.1.2 | Developer | 2024-08-08 | 2024-08-09 | 2024-08-10 | 7Hrs | Completed | 100 | Backend email handler created for contact form
4 | Week 4: Testing Phase
4.1 |  | Unit Testing | Homepage Responsiveness | Mobile and Tablet Testing | Task 2.1.1 | Developer | 2024-08-12 | 2024-08-13 | 2024-08-13 | 6Hrs | Completed | 100 | Tested across devices for consistent UI
4.2.1 |  | Functional Testing | Search Functionality |  | Task 3.1.2 | Developer | 2024-08-13 | 2024-08-15 | 2024-08-16 | 7Hrs | Completed | 100 | Tested for valid and invalid search inputs
4.2.2 |  |  | Test Contact Form | Email Response Validation | Task 3.2.1 | Developer | 2024-08-16 | 2024-08-17 | 2024-08-18 | 5Hrs | Completed | 100
5 | Week 5: Finalization
5.1.1 |  | Bug Fixing | Fix UI Bugs | Resolve Responsiveness Issues | Task 4.1.1 | Developer | 2024-08-19 | 2024-08-20 | 2024-08-23 | 10Hrs | Completed | 100 | Identified and fixed UI bugs on mobile
5.2.1 |  | Final Deployment | Up Hosting | Prepare Deployment Scripts | Task 4.2.2 | Developer | 2024-08-23 | 2024-08-25 | 2024-08-26 | 7Hrs | Completed | 100 | Deployed the website on hosting service
5.2.2 |  |  | Final QA | Run End-to-End Tests | Task 5.2.1 | Developer | 2024-08-26 | 2024-08-27 | 2024-08-28 | 5Hrs | Completed | 100 | Final quality assurance tests before go-live
5.3 |  | Project Closure | Create Project Documentation | Prepare Final Report | Task 5.2.2 | Developer | 2024-08-28 | 2024-08-29 | 2024-08-30 | 6Hrs | Completed | 100 | Finalized project documentation and closure report
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you