## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Web Development
INTERN NAME: | Atharv Musale
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 2024-08-28
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | Campus Search
PROJECT ID | IP-4024
INTERN NAME | Atharv Musale
PROJECT MANAGER | Harshada Topale
INTRODUCTION
The testing strategy for this project aims to ensure that the web application for college discovery functions smoothly, is user-friendly, and delivers accurate results. The process involves functional and non-functional testing methodologies. The workflow includes a step-by-step validation of each module of the application, from frontend to backend, covering search functionality, responsiveness, database interactions, and user experience. Manual testing will be employed, while bug tracking will be managed through regular review meetings to ensure all issues are resolved.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
Search functionality: Testing the ability to search colleges by name and retrieve accurate results. Data accuracy: Ensuring that the college information displayed (name, address, and contact details) is correct. Frontend testing: Validating UI/UX, responsiveness, and cross-browser compatibility. Navigation: Testing smooth transitions between pages (home, results, contact). Contact page functionality: Ensuring form submission is properly handled. Performance: Testing the speed and load time of the application across devices.
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
This test plan excludes testing third-party APIs, data from external sources, and any features or functionalities related to future updates or planned enhancements that are not currently implemented. Additionally, testing for accessibility compliance beyond basic usability will not be covered. This test plan excludes testing third-party APIs, data from external sources, and any features or functionalities related to future updates or planned enhancements that are not currently implemented. Additionally, testing for accessibility compliance beyond basic usability will not be covered.
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
Ensure that the Application Under Test (AUT) conforms to all functional and non-functional requirements. Verify that the application meets the client’s quality specifications and usability standards. Ensure that all bugs/issues are identified and fixed before the application goes live. Conduct a final review to confirm that no critical issues remain.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
QA Analyst: Responsible for executing manual test cases, identifying bugs, and validating fixes. Test Manager: Oversees the overall testing process, ensures timely execution, and allocates resources. Configuration Manager: Manages test environments, version control, and configuration settings for the application. Developers: Resolve identified bugs and implement any required fixes. Installation Team: Ensures the application is properly deployed in the test and production environments.
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
We are using a manual testing methodology due to the small-scale nature of the project. This allows for flexibility in handling bugs and real-time feedback. The method ensures that every part of the user interface and backend is thoroughly tested before deployment.
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
Unit Testing: Each individual function, such as search queries, will be tested for accuracy. Integration Testing: Ensuring that the frontend (search form, buttons) communicates with the backend (database) properly. System Testing: Testing the entire application end-to-end, covering functionality, performance, and usability. User Acceptance Testing (UAT): Testing by users to ensure that the system fulfills their needs.
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
Bugs will be categorized as Critical, High, Medium, or Low priority. Critical and High priority bugs must be resolved before the next phase of testing, while lower-priority bugs will be addressed in subsequent releases.
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
100% test coverage of all features. Execution of all manual test cases. All identified bugs are resolved, and no open critical bugs remain. All UI and functional requirements are validated.
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
1. Test Plan 2. Test Cases 3.Test Scripts 4. Test Data 5. Test Reports 6. Bug Reports 7. Test Summary Report
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
1. Hardware: Testing servers and computers 2. Software: Web browsers, OS, and database systems 3. Network: Internet and internal network access 4. Testing Tools: Bug tracking, test management, and automation tools
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Minimum: Windows 8+, 4 GB RAM, 500 GB storage. Browser compatibility: Chrome, Firefox, Edge. Mobile compatibility for responsive testing.
ADDITIONAL COMMENTS
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Search Functionality | Test search bar for correct results on college name input. | 2024-08-25 | 2024-08-25 | Developer | PASSED | None
Data Display Accuracy | Verify correct display of college name, city, and contact info. | 2024-08-25 | 2024-08-26 | Developer | PASSED | None
Navigation | Test smooth transitions between home, result, and contact page. | 2024-08-26 | 2024-08-26 | Developer | PASSED | None
UI/UX Responsiveness | Ensure UI works well across devices and screen sizes. | 2024-08-26 | 2024-08-26 | Developer | PASSED | None
Performance Testing | Check load time and responsiveness under varying conditions. | 2024-08-26 | 2024-08-27 | Developer | PASSED | None
Contact Page Functionality | Verify form submission and error handling. | 2024-08-27 | 2024-08-28 | Developer | FAILED | None
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.